## CSM
Tasks | Time estimation in Hours
1. Login Module | 12
1.1 UI Creation, Login functionality
1.2 Forgot password / Reset password functionality
1.3 Remember Me functionality
2. Home Screen | 16
2.1 UI Creation
2.2 Dashboard
2.3 Show all Stats
3. User Profile | 8
3.1 View / Edit / Update profile
3.2 Logout
4. User Module | 16
4.1 View / Edit / Update users
5. Vehicle Record Module | 12
5.1 View / Edit / Update
6. Ride Module | 16
6.1 View / Edit / Update
7. Driver Trip management Module | 20
7.1 View / Edit / Update drivers
7.2 Driver trip management
7.3 Driver current location
8. Driver Voucher Module | 24
8.1 Create / view / edit / update
8.2 Driver voucher management / purchase
9. User promo codes Module | 25
9.1 Create / view / edit / update
9.2 User voucher management / deploye
10. User / Driver feedback Module | 20
10.1 User feedback / reponse module
10.2 Driver feedback / reponse module
11. Push Notification Module | 15
11.1 User / Driver push notification
12.Frontend website | 32
12.1 Pages module
12.2 Contact Us Module
12.3 User / Driver Registration form
12.4 Home page view
12.5 Menu Management
13.Payment Transaction module | 16
13.1 Transaction history
14. Social media integration | 16
14.1 single sign in
14.2 user data management
15. Mobile verification otp integration | 8
16. Fare calculation integration | 10
17. User Card details integration | 12
Total | 278

## API
Mobile API's | Time estimation in Hours
User API
login | 3
social login | 6
register / device to token / reference code | 6
mobile opt api | 4
ride history | 2
card detail | 3
user detail api | 2
promotion code api | 4
user home screen location ( current location ) | 2
drivers location at user current location | 4
cab type | 1
book ride | 3
fare estimated / distance / time / driver details / vehicle detail / avg rating of driver | 8
ongoing ride api / driver current location | 2
ride finish | 1
transaction detail | 3
rating / feedback user | 3
user reference code validate | 3
ride cancel | 1
reschedule ride | 3
push notification | 5
pages / faq content | 3
rate card | 3
vehicle current location to user | 2
Driver API
driver current location | 2
ride request | 3
ride accept | 2
user details | 2
cancel ride | 1
start ride | 2
voucher purchase | 5
ride history | 2
voucher details | 2
promo code / reference code | 5
transaction history | 3
code verification | 3
voucher history | 2
rating / feedback driver | 2
Total | 113